## Project Team
Project Name: AWS CyberShift Initiative Client: OzCasual Vendor: SecureNET
Project Team Member | Role
Hettige Jayatissa | Business Owner
Giuseppe Raciti | Project Manager
Mark Byrne | Cloud Architect / Engineer
Shaun Heywood | Cyber Security Specialist
Mauricio Guerra | Server Administrator

## High Level WBS & Burnup
Project Plan: AWS CyberShift Initiative Client: OzCasual Vendor: SecureNET
Project Planning
Task ID | Task | Due Date | Planned Tasks | Actual tasks | Planned Cumulative | Actual Cumulative
1.1 | Project Requirments Definition | 2023-06-13 | 1 | 1 | 68 | 68
1.2 | Define Project Scope | 2023-06-17 | 1 | 3 | 67 | 65
1.3 | Assemble Project Team | 2023-06-18 | 3 | 3 | 64 | 62
1.4 | Develop Work Breakdown Structure | 2023-06-19 | 2 | 3 | 62 | 59
1.5 | Develop Project Plan | 2023-06-21 | 6 | 5 | 56 | 54
1.6 | Finalise Project Plan and Obtain Approval | 2023-06-25 | 1 | 1 | 55 | 53
Project Implementation |  |  |  |  | 55 | 53
2.1 | ReConfigure Network Infrastructure | 2023-06-25 | 8 | 8 | 47 | 45
2.2 | Install/Upgrade Application Systems | 2023-06-25 | 6 | 4 | 41 | 41
2.3 | Install & Configure Security Systems | 2023-06-25 | 6 | 4 | 35 | 37
2.4 | Develop Formal End-to-End Test Plans | 2023-07-02 | 5 | 10 | 30 | 27
2.5 | Execute End-to-End Testing & Remedy Deficiencies | 2023-07-02 | 4 | 2 | 26 | 25
2.6 | Finalise New System Operational/Support Processes & Documentation | 2023-07-07 | 4 | 2 | 22 | 23
Project Review |  |  |  |  | 22 | 23
3.1 | Handover Documentation | 2023-07-07 | 5 | 5 | 17 | 18
3.2 | Review Project Team Performance | 2023-07-10 | 5 | 0 | 12 | 18
3.3 | Execute Red-Blue Testing | 2023-07-10 | 6 | 0 | 6 | 18
3.4 | Obtain Sign-Off & Close Project | 2023-07-14 | 6 | 0 | 0 | 18
|  |  | 69 | 51

## Project Timeline & Milestones
Project Plan: AWS CyberShift Initiative Client: OzCasual Vendor: SecureNET
Key Project Milestones
| Date | Milestone | Column1 | Position | Baseline
| 2023-06-05 | Project Start |  | 20 | 0
| 2023-06-09 | Project Sign-off |  | 12 | 0
| 2023-06-10 | Sprint One Start |  | -10 | 0
| 2023-06-23 | Sprint One Complete |  | 20 | 0
| 2023-06-24 | Project Plan Approved |  | 5 | 0
| 2023-06-24 | Sprint Two Start |  | -15 | 0
| 2023-07-07 | Sprint Two Complete |  | 15 | 0
| 2023-07-08 | Sprint Three Start |  | -15 | 0
| 2023-07-14 | Sprint Three Complete |  | 10 | 0
| 2023-07-15 | Project End |  | -5 | 0
Formulas:
Date = [Date, row above]+13

## Detailed WBS
Project Plan: AWS CyberShift Initiative Client: OzCasual Vendor: SecureNET
Planning - Sprint One
Implementation - Sprint Two
Documentation - Sprint Three

## Project Schedule & Gantt Chart
Project Plan: AWS CyberShift Initiative Client: OzCasual Vendor: SecureNET
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | AWS CyberShift Initiative
Enter Company Name in cell B2. | SecureNET
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Project Start: label is in cell C3. | Giuseppe Raciti | Project Start: |  | 2023-06-05
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Display Week: |  | 1 |  |  | 2023-06-05 | [6 empty] | 2023-06-12 | [6 empty] | 2023-06-19 | [6 empty] | 2023-06-26 | [6 empty] | 2023-07-03 | [6 empty] | 2023-07-10 | [6 empty] | 2023-07-17 | [6 empty] | 2023-07-24
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2023-06-05 to 2023-07-30
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK |  | PROGRESS | START | END | DAYS | time axis 2023-06-05 to 2023-07-30
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Sprint 1 - Project Planning
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progress of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | Define Stakeholders |  | 100% | 2023-06-05 | 2023-06-08 | 4
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | Project Sign-off |  | 100% | 2023-06-08 | 2023-06-10 | 3
| Define Project Scope |  | 100% | 2023-06-10 | 2023-06-12
| Define ways of working |  | 100% | 2023-06-12 | 2023-06-14
| Define KPIs |  | 100% | 2023-06-14 | 2023-06-16
| Define detailed WBS |  | 100% | 2023-06-14 | 2023-06-18
| Develop Project schedule |  | 100% | 2023-06-14 | 2023-06-18
| Develop Project Budget |  | 100% | 2023-06-14 | 2023-06-18
| Develop task recording and reporting |  | 100% | 2023-06-15 | 2023-06-17
| Budget Mgt Plan |  | 100% | 2023-06-17 | 2023-06-19
| Schedule Mgt Plan |  | 100% | 2023-06-19 | 2023-06-21
| Quality Mgt Plan |  | 100% | 2023-06-18 | 2023-06-20
| Risk Mgt Plan |  | 100% | 2023-06-12 | 2023-06-16
| Communications Mgt Plan |  | 100% | 2023-06-13 | 2023-06-17
| Scope Mgt Plan |  | 100% | 2023-06-17 | 2023-06-19
| Develop Project Charter |  | 100% | 2023-06-14 | 2023-06-21
| Obtain Project Plan approval |  | 100% | 2023-06-21 | 2023-06-21
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Sprint Two - Implementation
| Develop network topology - current |  | 100% | 2023-06-20 | 2023-06-24 | 5
| Develop asset register |  | 100% | 2023-06-24 | 2023-06-24 | 1
| Develop redesign network topology |  | 100% | 2023-06-23 | 2023-06-25
| Reconfigure existing HW |  | 100% | 2023-06-25 | 2023-06-27
| Upgrade current application systems (if reqiuired) |  | 100% | 2023-06-26 | 2023-06-28
| Add pfSense to Windows AD Server |  | 100% | 2023-06-28 | 2023-07-02
| Add Snort for IPS to Windows AD Server |  | 100% | 2023-06-28 | 2023-07-02
| Add Sophois for Anit-virus to Windows AD Server |  | 100% | 2023-06-28 | 2023-07-02
| Add Splunk for Log analysis to Windows AD Server |  | 100% | 2023-06-28 | 2023-07-02
| Add Wireshark for RT monitoring to Windows AD Server |  | 100% | 2023-06-28 | 2023-07-02
| Add Sophos for Firewall to Linux Web Server |  | 100% | 2023-07-01 | 2023-07-04
| Add Snort for IPS to Linux Web Server |  | 100% | 2023-07-01 | 2023-07-04
| Add Sophos Intercept X for Anit-virus protection to Linux Web Server |  | 100% | 2023-07-01 | 2023-07-04
| Add Splunk for Log monitoring to Linux Web Server |  | 100% | 2023-07-01 | 2023-07-04
| Add Wireshark for RT monitoring to Linux Web Server |  | 100% | 2023-07-01 | 2023-07-04
| Develop Test Plans for Server Traffic Monitors |  | 100% | 2023-06-29 | 2023-07-05
| Develop Test Plans for Server Log Analysis systems |  | 100% | 2023-06-29 | 2023-07-05
| Develop Test Plans for Server Anti-Virus systems |  | 100% | 2023-06-29 | 2023-07-05
| Develop Test Plans for Server Firewalls |  | 100% | 2023-06-29 | 2023-07-05
| Conduct test for Server Traffic Monitors |  | 100% | 2023-07-05 | 2023-07-06
| Conduct test for Server Log Analysis systems |  | 100% | 2023-07-05 | 2023-07-06
| Conduct test for Server Anti-Virus systems |  | 100% | 2023-07-05 | 2023-07-06
| Conduct test for Server Firewalls |  | 100% | 2023-07-05 | 2023-07-06
| Develop procedures for Start-up |  | 100% | 2023-06-30 | 2023-07-03
| Develop procedures for Shut down |  | 100% | 2023-06-30 | 2023-07-03
| Develop procedures for back-up and recovery |  | 100% | 2023-06-30 | 2023-07-05 | 6
| Develop procedures for Maintenance and schedule |  | 100% | 2023-07-05 | 2023-07-05 | 1
Sample phase title block | Sprint Three - Documentation & Review
| Document Start-up operations |  | 100% | 2023-06-30 | 2023-07-03 | 4
| Document Shutdown operations |  | 100% | 2023-06-30 | 2023-07-03
| Document Maintenence Procedures |  | 100% | 2023-07-01 | 2023-07-03
| Document Backup procedures |  | 100% | 2023-06-30 | 2023-07-03
| Document Training material |  | 5% | 2023-07-01 | 2023-07-03
| Create DDoS Runbook |  | 100% | 2023-07-05 | 2023-07-06
| Create Brute Force Runbook |  | 100% | 2023-07-07 | 2023-07-10
| Create Malware Runbook |  | 100% | 2023-07-09 | 2023-07-12
| Execute training for DDoS Attack |  | 0% | 2023-07-09 | 2023-07-10
| Execute training for Brute Force Attack |  | 0% | 2023-07-09 | 2023-07-10
| Execute training for Malware Attack |  | 0% | 2023-07-09 | 2023-07-10
| Create Final Report |  | 0% | 2023-07-11 | 2023-07-14
| Create Final Presentation |  | 0% | 2023-07-11 | 2023-07-14
| Prepare signoff document |  | 0% | 2023-07-15 | 2023-07-15 | 1
| Project Sign-off |  | 0% | 2023-07-16 | 2023-07-16 | 1
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html

## Project Budget
Project Plan: AWS CyberShift Initiative Client: OzCasual Vendor: SecureNET
Task | Assigned To | Planned Hours | Actual Hours | Unit cost | Budgeted Cost | Actual Cost | Variance to Budget | Comments
Sprint One
Task 1.1 - Project Requirements Definition
1.1 - Define Stakeholders and Information Sources | Giuseppe Raciti | 3 | 3 | 150 | 450 | 450 | 0
1.1 - Project Requirements Definition | Giuseppe Raciti | 4 | 4 | 150 | 600 | 600 | 0
Task 1.2 - Define Project Scope
1.2 - Define the Project Scope | Giuseppe Raciti | 4 | 4 | 150 | 600 | 600 | 0
Task 1.3 - Assemble Project Team & Allocate Responsibilities
1.3 - Discuss ways of working and arrangements to meet | All | 1 |  | 150 | 150 | 0 | -150
1.3 - Define KPIs for each role/responsibility | Mauricio Guerra | 3 | 4 | 150 | 450 | 600 | 150 | 3 Revisions
1.3 - Allocate roles and responsibilities to each of the individuals | Mauricio Guerra | 1 | 1 | 150 | 150 | 150 | 0
1.3 - Define KPIs for project team as a whole | Mauricio Guerra | 2 | 2 | 150 | 300 | 300 | 0
Task 1.4 - Develop Work Breakdown Structure & Allocate Resources
1.4 - Develop the full WBS to the individual Work Package level | Mark Byrne | 3 | 4 | 150 | 450 | 600 | 150
1.4 - Prepare the project schedule and a draft project budget | Mark Byrne | 4 | 5 | 150 | 600 | 750 | 150
1.4 - Prepare a form for recording and reporting team member's allocated duties | Mark Byrne | 2 | 1 | 150 | 300 | 150 | -150
Task 1.5 - Prepare Scope, Quality, Budget, Schedule, Comms Management Plans
1.5 - Budget Management Plan | Mark Byrne | 3 | 3 | 150 | 450 | 450 | 0
1.5 - Schedule Management Plan | Mark Byrne | 3 | 3 | 150 | 450 | 450 | 0
1.5 - Quality Management Plan | Shaun Heywood | 3 | 4 | 150 | 450 | 600 | 150
1.5 - Risk Management Plan | Shaun Heywood | 3 | 4 | 150 | 450 | 600 | 150
1.5 - Communications Management Plan | Mauricio Guerra | 3 | 3 | 150 | 450 | 450 | 0
1.5 - Scope Management Plan | Giuseppe Raciti | 3 | 2 | 150 | 450 | 300 | -150
1.5 - Project Charter | Giuseppe Raciti | 3 | 3 | 150 | 450 | 450 | 0
Task 1.6 - Finalise Project Plan and Obtain Approval
1.6 - Finalise Project Plan & Obtain Approval | Hettige Jayatissa | 3 |  | 150 | 450 | 0 | -450
Subtotal |  | 48 | 50 |  | 7650 | 7500 | -150
Sprint Two
Task 2.1 - ReConfigure Network Infrastructure
2.1 - Produce configuration management records |  | 2 | 2 | 150 | 300 | 300 | 0
2.1 - Reconfigure existing network infrastructure |  | 5 | 3 | 150 | 750 | 450 | -300
2.1 - Redesign the network topology including topology diagrams with per-port addressing |  | 3 | 3 | 150 | 450 | 450 | 0
2.1 - Installation/removal of new/existing network equipment |  | 5 | 3 | 150 | 750 | 450 | -300
2.1 - Reconfiguration of existing equipment |  | 3 | 3 | 150 | 450 | 450 | 0
2.1 - Introduction of new security procedures/practices/facilities |  | 4 | 8 | 150 | 600 | 1200 | 600
2.1 - Execute your test plans for each piece of routing/switching/fire-walling infrastructure |  | 4 | 12 | 150 | 600 | 1800 | 1200
2.1 - Produce appropriate configuration management records for your new network infrastructure |  | 4 | 2 | 150 | 600 | 300 | -300
Task 2.2 - Install/Upgrade Application Systems
2.2 - Install or upgrade all current OZCazual application systems |  | 4 | 10 | 150 | 600 | 1500 | 900
2.2 - Upgrade existing systems in the new infrastructure |  | 4 | 7 | 150 | 600 | 1050 | 450
2.2 - Install new systems to replace the existing application systems |  | 5 | 5 | 150 | 750 | 750 | 0
2.2 - Install additional systems to further enhance the security of the infrastructure |  | 3 | 20 | 150 | 450 | 3000 | 2550
2.2 - Execute your unit test plans for each application system |  | 4 | 7 | 150 | 600 | 1050 | 450
2.2 - Produce appropriate configuration management records for the application systems |  | 4 | 2 | 150 | 600 | 300 | -300
Task 2.3 - Install & Configure Security Systems
2.3 - Implement Server Traffic Monitors |  | 3 | 5 | 150 | 450 | 750 | 300
2.3 - Implement Log analysis systems |  | 3 | 12 | 150 | 450 | 1800 | 1350
2.3 - Implement Anti-Virus/Malware systems |  | 3 | 5 | 150 | 450 | 750 | 300
2.3 - Implement Internal Firewalls |  | 3 | 7 | 150 | 450 | 1050 | 600
2.3 - Implement resources for remediation of compromised systems in the event of a cyber incident |  | 3 | 3 | 150 | 450 | 450 | 0
2.3 - Execute unit test plans for all components of your Security systems |  | 4 | 4 | 150 | 600 | 600 | 0
Task 2.4 - Develop Formal End-to-End Test Plans
2.4 - Develop end-to-end test plans for Server Traffic Monitors |  | 4 | 8 | 150 | 600 | 1200 | 600
2.4 - Develop end-to-end test plans for Log analysis systems |  | 4 | 4 | 150 | 600 | 600 | 0
2.4 - Develop end-to-end test plans for Anti-Virus/Malware systems |  | 4 | 4 | 150 | 600 | 600 | 0
2.4 - Develop end-to-end test plans for Internal Firewalls |  | 4 | 4 | 150 | 600 | 600 | 0
2.4 - Obtain agreement from line-of-business managers that the test plans are adequate |  | 2 | 1 | 150 | 300 | 150 | -150
Task 2.5 - Execute End-to-End Testing & Remedy Deficiencies
2.5 - Server Traffic Monitors |  | 4 | 1 | 150 | 600 | 150 | -450
2.5 - Log Analysis Systems |  | 4 | 1 | 150 | 600 | 150 | -450
2.5 - Anti-Virus/Malware systems |  | 4 | 2 | 150 | 600 | 300 | -300
2.5 - Internal Firewalls |  | 4 | 2 | 150 | 600 | 300 | -300
Task 2.6 - Finalise New System Operational/Support Processes & Documentation
2.6 - Start-up & shutdown procedures |  | 2 | 2 | 150 | 300 | 300 | 0
2.6 - Backup & recovery from backup procedures |  | 2 | 2 | 150 | 300 | 300 | 0
2.6 - Regular maintenance activities with a schedule of execution |  | 2 | 2 | 150 | 300 | 300 | 0
2.6 - Produce a final report for the system designed |  | 2 | 9 | 150 | 300 | 1350 | 1050
Subtotal |  |  |  |  | 17250 | 24750 | 7500
Sprint Three
Task 3.1 - Prepare Handover Documentation
3.1 - Prepare handover documentation for Start-up operations |  | 1 | 1 | 150 | 150 | 150 | 0
3.1 - Prepare handover documentation for shutdown operations |  | 1 | 1 | 150 | 150 | 150 | 0
3.1 - Prepare handover documentation for regular maintenance procedures |  | 1 | 1 | 150 | 150 | 150 | 0
3.1 - Prepare handover documentation for Backup procedures |  | 1 | 1 | 150 | 150 | 150 | 0
3.1 - Prepare handover documentation for Training requirements for OzCazual staff |  | 1 | 2 | 150 | 150 | 300 | 150
Task 3.2 - Review Project Team Performance
3.2 - Performance of team members |  | 4 | 3 | 150 | 600 | 450 | -150
3.2 - Recognition of individual's achievements |  | 2 | 2 | 150 | 300 | 300 | 0
3.2 - Execution of the project against project plans |  | 1 | 2 | 150 | 150 | 300 | 150
3.2 - Archive project records and correspondence |  | 1 | 1 | 150 | 150 | 150 | 0
3.2 - Document Project Management Lessons Learned through the management of the project |  | 2 | 1 | 150 | 150 | 150 | 0
Task 3.3 - Execute Red-Blue Testing
3.3 - Develop Red-Blue testing exercise and execute it train OzCazual staff |  | 5 | 10 | 150 | 750 | 1500 | 750
3.3 - Develop DDoS Run-book |  | 5 | 8 | 150 | 750 | 1200 | 450
3.3 - Perform scans & attacks using DDoS attack |  | 5 | 1 | 150 | 750 | 150 | -600
3.3 - Perform scans & attacks using Brute force Attack (SSH) |  | 5 | 1 | 150 | 750 | 150 | -600
3.3 - Perform scans & attacks using Virus/Malware |  | 5 | 2 | 150 | 750 | 300 | -450
3.3 - Record the results of the scans and attacks to be used in the final presentation |  | 4 | 1 | 150 | 600 | 150 | -450
Task 3.4 - Obtain Sign-Off & Close Project
3.4 - Prepare results of the Red-Blue team exercises to add to the presentation |  | 5 | 2 | 150 | 750 | 300 | -450
3.4 - Feedback to the system designer regarding modifications to the original design to be included in the presentation |  | 4 | 2 | 150 | 600 | 300 | -300
3.4 - Prepare a report that outlines the remaining exposure to cyber security incidents |  | 5 | 3 | 150 | 750 | 450 | -300
3.4 - A report that details the delivery of project goals for the presentation |  | 5 | 4 | 150 | 750 | 600 | -150
3.4 - Create a presentation of the project for the sponsor |  | 5 | 6 | 150 | 750 | 900 | 150
3.4 - Prepare a formal sign-off document for the project sponsor to complete | Hettige Jayatissa | 2 | 1 | 150 | 300 | 150 | -150
Subtotal |  |  |  |  | 10350 | 8400 | -1950
Total |  |  |  |  | 35250 | 40650 | 5400